## Blad1
wetenschappelijk project
| Car to car connection |  |  | PLANNING |  |  | VOORTGANG |  |  | INHOUD |  |  | OPMERKINGEN
TAKEN |  |  |  | GEPLANDE UITVOERING |  |  | WERKELIJKE UITVOERING |  |  | INHOUDELIJKE INFORMATIE (links)
ref nr. | taak/onderzoeksvraag | deeltaak/deelvraag | status | startdatum | einddatum | uitvoerder | startdatum | einddatum | uitvoerder | lokale documenten | websites | verslagen
10 | Ideas
11 |  | Acoustic levitation | A | 2018-02-21 | 2018-02-28 | Gauthier de Borrekens | 2018-08-21 | 2018-02-28 | Gauthier de Borrekens |  |  | 1-Gauthier de Borrekens-Levitation
12 |  | Car to car communication | A | 2018-02-21 | 2018-02-28 | Satish Singh | 2018-08-21 | 2018-02-28 | Satish Singh |  |  | 1-Satish Singh-RcCars
13 |  | Smart room /w noise cancellation | A | 2018-02-21 | 2018-02-28 | Ali Amir | 2018-08-21 | 2018-02-28 | Ali Amir |  |  | 1-Ali Amir-SmartRoom
13 |  | RFID security | A | 2018-02-21 | 2018-02-28 | Daniel Smetankin | 2018-08-21 | 2018-02-28 | Daniel Smetankin |  |  | 1-Daniel Smetankin-RFID
14 |  | Blockchain data security | A | 2018-02-21 | 2018-02-28 | Asif Wasefi | 2018-08-21 | 2018-02-28 | Asif Wasefi
20 | Research ¦ Case study
21 |  | Connection (UDP) | A | 2018-02-28 | 2018-03-07 | Daniel Smetankin | 2018-02-28 | 2018-03-07 | Daniel Smetankin |  |  | 2-Daniel Smetankin-Connection
22 |  | nodeMCU | A | 2018-02-28 | 2018-03-07 | Gauthier de Borrekens | 2018-02-28 | 2018-03-07 | Gauthier de Borrekens |  |  | 2-Gauthier de Borrekens-NodeMCU
23 |  | RC Car | A | 2018-02-28 | 2018-03-07 | Satish Singh | 2018-02-28 | 2018-03-07 | Satish Singh |  |  | 2-Satish Singh-Car
24 |  | Radio controller | A | 2018-02-28 | 2018-03-07 | Ali Amir | 2018-02-28 | 2018-03-07 | Ali Amir |  |  | 2-Ali Amir-RadioControl
25 |  | PC Server | A | 2018-02-28 | 2018-03-07 | Asif Wasefi | 2018-02-28 | 2018-03-07 | Asif Wasefi |  |  | 2-Asif Wasefi-Server
26 | Documentation analysis
27 |  | UDP vs TCP | A | 2018-03-07 | 2018-03-14 | Daniel Smetankin Smetakin | 2018-03-07 | 2018-03-14 | Daniel Smetankin |  |  | 3_Daniel Smetankin_different_comm_protocols
28 |  | NodeMCU vs Other Microchips | A | 2018-03-07 | 2018-03-14 | Gauthier de Borrekens | 2018-03-07 | 2018-03-14 | Ali Amir |  |  | 3_Ali Amir_NodeMCU-programming
29 |  | RC Car (type) vs other type | A | 2018-03-07 | 2018-03-14 | Satish Singh | 2018-03-07 | 2018-03-14 | Satish Singh |  |  | 3_Satish Singh_RCCarVsOtherCars
30 |  | Server Choice vs other servers | A | 2018-03-07 | 2018-03-14 | Asif Wasefi | 2018-03-07 | 2018-03-14 | Asif Wasefi |  | Linux_Timeline | 3_Asif Wasefi_Server_OS_comparison
31 |  | WiFi vs other communications | A | 2018-03-07 | 2018-03-14 | Ali Amir | 2018-03-07 | 2018-03-14 | Gauthier de Borrekens |  |  | 3_Gauthier de Borrekens_Different-Microcontrollers
32 | Theoretical Check
33 |  | Server Software, connection with nodeMCU | A | 2018-03-14 | 2018-03-21 | Asif Wasefi | 2018-03-14 | 2018-03-21 | Asif Wasefi |  |  | 4 Asif Wasefi Server_connection_nodeMCU
34 |  | Motor Programming | A | 2018-03-14 | 2018-03-21 | Daniel Smetankin Smetakin, Satish Singh | 2018-03-14 | 2018-03-21 | Daniel Smetankin |  |  | 4 Daniel Smetankin WP_Motor_Programming
35 |  | Arduino IDE | A | 2018-03-14 | 2018-03-21 | Gauthier de Borrekens, | 2018-03-14 | 2018-03-21 | Gauthier de Borrekens |  |  | 4 Gauthier de Borrekens21_03 ESP8266 Programming
|  | Send UDP packet to other devices Ubuntu | A | 2018-03-14 | 2018-03-21 | Ali Amir | 2018-03-14 | 2018-03-21 | Ali Amir |  |  | 4 Ali Amir NodeMCU-UDP
|  | Voltage stabilizer | U | 2018-03-14 | 2018-03-21 | Satish Singh
36 | Pracitcal work
37 |  | Time calculation UDP packet transmitting | A | 2018-03-21 | 2018-03-28 | Asif Wasefi | 2018-03-21 | 2018-03-28 | Asif Wasefi |  |  | 5-Asif Wasefi Measuring UDP latency
38 |  | Microcontroller Software: SR04 | A | 2018-03-21 | 2018-03-28 | Gauthier de Borrekens | 2018-03-21 | 2018-03-28 | Gauthier de Borrekens |  |  | 5-Gauthier de Borrekens sonar ranging module
39 |  | Statistics of measurements | A | 2018-03-21 | 2018-03-28 | Ali Amir | 2018-03-21 | 2018-03-28 | Ali Amir |  |  | 5-CurrentsAndVoltages-SS-AA
40 |  | Are all the voltages of the components correct | A | 2018-03-21 | 2018-03-28 | Satish Singh | 2018-03-21 | 2018-03-28 | Satish Singh |  |  | 5-CurrentsAndVoltages-SS-AA
|  | Voltage stabilizer | A | 2018-03-14 | 2018-03-28 | Satish Singh | 2018-03-21 | 2018-03-28 | Satish Singh |  |  | 5-poweringOfNodeMCU-SS
|  | Integration H-bridge into motor programming | A | 2018-03-21 | 2018-03-28 | Daniel Smetankin | 2018-03-21 | 2018-03-28 | Daniel Smetankin |  |  | 5-WP_Motor_Programming_Daniel Smetankin_SmetankinV2
50 | Poster
51 |  | Concepts | A | 2018-04-11 | 2018-04-18 | Group | 2018-04-11 | 2018-04-18
|  |  | A | 2018-04-11 | 2018-04-18 |  | 2018-04-11 | 2018-04-18 | Asif Wasefi |  |  | 6-Asif Wasefi How to make a scientific poster
|  |  | A | 2018-04-11 | 2018-04-18 |  | 2018-04-11 | 2018-04-18 | Ali Amir |  |  | 6-Ali Amir PosterProposition
|  |  | A | 2018-04-11 | 2018-04-18 |  | 2018-04-11 | 2018-04-18 | Satish Singh
52 | Designing actual poster
53 |  | x |  | 2018-04-18 | 2018-04-25
54 |  | x |  | 2018-04-18 | 2018-04-25
55 |  | x |  | 2018-04-18 | 2018-04-25
56 |  | x |  | 2018-04-18 | 2018-04-25
57 | Afterwork
58 |  | Poster concept | A | 2018-04-25 | 2018-05-02 |  | 2018-04-25 | 2018-05-02 | Asif Wasefi, Satish Singh
59 |  | ActuAli Amirsation + information poster | A | 2018-04-25 | 2018-05-02 |  | 2018-04-25 | 2018-05-02 | Satish Singh |  |  | 7-Satish Singh_Poster+ideaFormulation
60 |  | Lasercutting | A | 2018-04-25 | 2018-05-02 |  | 2018-04-25 | 2018-05-02 | Ali Amir |  |  | 7-Ali Amir_Lasercutter
61 |  | Software updates | A | 2018-04-25 | 2018-05-02 |  | 2018-04-25 | 2018-05-02 | Gauthier de Borrekens |  |  | 7-Gauthier de Borrekens_SoftwareUpdates
62 |  | Inrushcurrent | A | 2018-04-25 | 2018-05-02 |  | 2018-04-25 | 2018-05-02 | Daniel Smetankin |  |  | 7-Daniel Smetankin_Inrushcurrent
62 | extreme fine tuning
63 |  | Content modules | A | 2018-05-02 | 2018-05-09 | Gauthier de Borrekens | 2018-05-02 | 2018-05-09 | Gauthier de Borrekens |  |  | 8-Gauthier de Borrekens_poster_ideas
64 |  | Poster design | A | 2018-05-02 | 2018-05-09 | Daniel Smetankin | 2018-05-02 | 2018-05-09 | Daniel Smetankin |  |  | 8-Daniel Smetankin_poster_design
65 |  | 2 other cars from scratch | A | 2018-05-02 | 2018-05-09 | Ali Amir,Satish Singh | 2018-05-02 | 2018-05-09 | Ali Amir,Satish Singh |  |  |  | Practical work which was completed by Satish and Ali
66 |  | Administration | U | 2018-05-02 | 2018-05-09 | Asif Wasefi | [6 empty] | There were a few documents needed to be corrected. For example converting to PDF, deleting tekst in Dutch, using the right template, … Not all the needed tasks have been done as of 09/05/2018. This task shall be delayed until next week.
67 |  | Content modules | A | 2018-05-02 | 2018-05-09 | Asif Wasefi | 2018-05-02 | 2018-05-09 | Asif Wasefi |  |  | 8-Asif Wasefi_poster_ideas
Weekly Reports
| Week1 (28/02/2018) | Report1 |  |  |  | Gauthier
| Week2 (07/03/2018) | Report2 |  |  | Missing | 1
| Week3 (14/03/2018) | Report3 |  |  | There is a pdf, which seems like a preparation. But there is no report of this date. | 2
| Week4(21/03/2018) | Report4 |  |  |  | Asif
| Week5(28/03/2018) | Report5 |  |  | Missing | 3
| Week6(18/04/2018) | Report6 |  |  |  | Ali
| Week7(25/04/2018) | Report7 |  |  |  | Gauthier
| Week8(02/05/2018) | Report8 |  |  |  | Daniel
| Week9(09/05/2018) | Report9
Note on C4: Plaats hier de naam van je project
Note on C7: de naam van een taak kan vervangen worden door een onderzoeksvraag
Note on E7: G : gestart (geel) A: afgewerkt (groen) U : uitgesteld (rood) (gebruik van de celopvulkleur geeft een beter overzicht op de status
Note on C16: plaats hier de naam van de uit tevoeren taak
Note on D17: plaats hier de naam van de uit te voeren deeltaak
Note on D18: plaats hier de naam van de uit te voeren deeltaak
Note on D19: plaats hier de naam van de uit te voeren deeltaak